## jira
Kfir Bilu 205639230, Dor Zaneti 204610984, Chen Gleicher 201050135
Status | Due Date | Start Date | Task | Subject | Sprint | Weekly subject | week
Done | 4.4.21 | 21.3.21 | Assign tasks for each team member | Preparations (Milestone 1) | Sprint 1 | מתודולוגיות לפיתוח תוכנה , מהדרים וסביבות ריצה ותכנות מקבילי באמצעות ת'רדים | 1-3
Done | 4.4.21 | 21.3.21 | Creating sprints follow the user stories and learning curve
Done | 4.4.21 | 21.3.21 | Preparations
Done | 4.4.21 | 21.3.21 | Read and understand user stories
Done | 10.4.21 | 5.4.21 | Flight detection algorithms | Algorithms | Sprint 2
Done | 10.4.21 | 5.4.21 | Hybrid
Done | 10.4.21 | 5.4.21 | Linear
Done | 10.4.21 | 5.4.21 | Z-score
Done | 14.4.21 | 11.4.21 | Creating plug-ins | Plug-ins | Sprint 3
Done | 14.4.21 | 11.4.21 | Hybrid plug-in
Done | 14.4.21 | 11.4.21 | Linear regression plug-in
Done | 14.4.21 | 11.4.21 | Z-score plug-in
Done | 17.4.21 | 14.4.21 | Class files support class | Loading Files | Sprint 4 | חופשת פסח | 4
Done | 17.4.21 | 14.4.21 | Convert CSV to XML and load to app
Done | 17.4.21 | 14.4.21 | CSV support class
Done | 17.4.21 | 14.4.21 | The students wants to load XML,CSV AND Class files
Done | 17.4.21 | 14.4.21 | XML support class
Done | 17.4.21 | 14.4.21 | Determining columns names | XML Files Editing | Sprint 5
Done | 17.4.21 | 14.4.21 | Eyal wants do define the CSV file data that will dictate the flight behavior
Done | 17.4.21 | 14.4.21 | Save updated CSV file name, Anomaly detector algorithm's file path
Done | 17.4.21 | 14.4.21 | Set observation rate
Done | 17.4.21 | 14.4.21 | Updating min. and max. values for each column
To Do | 24.4.21 | 18.4.21 | Creating controls | Control Pannel | Sprint 6 | תכנות מוכוון אירועים עם GUI, JAVAFX | 5
To Do | 24.4.21 | 18.4.21 | Flight altitude clock
To Do | 24.4.21 | 18.4.21 | Flight direction clock
To Do | 24.4.21 | 18.4.21 | Flight speed clock
To Do | 24.4.21 | 18.4.21 | If the FlightGear is not open, countiue showing the flight altitude on the dashboard
To Do | 24.4.21 | 18.4.21 | If the FlightGear is open, the flight data at the current time point will be displayed
Done | 24.4.21 | 18.4.21 | Rudder displayed as a horizontal scroll bar
Done | 24.4.21 | 18.4.21 | The file will display the pitch, roll and yaw parameters
To Do | 24.4.21 | 18.4.21 | The user controls the flight records
Done | 24.4.21 | 18.4.21 | Throttle displayed as vertical scroll bar
To Do | 24.4.21 | 18.4.21 | "Choose algorithm" button | Buttons | Sprint 7 | MVC | 6
Done | 24.4.21 | 18.4.21 | "Forward" button
To Do | 24.4.21 | 18.4.21 | "Open Class file" button
To Do | 24.4.21 | 18.4.21 | "Open CSV file" button
To Do | 24.4.21 | 18.4.21 | "Open XML file" button
Done | 24.4.21 | 18.4.21 | "Pause" button
Done | 24.4.21 | 18.4.21 | "Rewind" button
To Do | 24.4.21 | 18.4.21 | "Speed" button (values between 0.25-2)
Done | 24.4.21 | 18.4.21 | "Stop" button
To Do | 24.4.21 | 18.4.21 | Creating buttons to control the app
Done | 24.4.21 | 18.4.21 | scroll bar / slider
To Do | 24.4.21 | 18.4.21 | "Details missing" error | Messages | Sprint 8
To Do | 24.4.21 | 18.4.21 | "Exception occurred" message
To Do | 24.4.21 | 18.4.21 | "File Load Success" message
To Do | 24.4.21 | 18.4.21 | "Wrong Class file input" (not a Class file)
To Do | 24.4.21 | 18.4.21 | "Wrong CSV file input" (not a CSV file)
To Do | 24.4.21 | 18.4.21 | "Wrong XML file input" (not a XML file)
To Do | 24.4.21 | 18.4.21 | Error / Success messages if something goes wrong while loading files
To Do | 24.4.21 | 18.4.21 | If exception occurs on a specific coordinate, flag it
To Do | 4.5.21 | 25.4.21 | Create UML design | Milestone 2 | Sprint 9 | MVVM | 7
To Do | 4.5.21 | 25.4.21 | Split UML into layers
To Do | 4.5.21 | 25.4.21 | UML design
To Do | 4.5.21 | 25.4.21 | Saving the last data updated | Save data | Sprint 10 | D.B Access | 8
To Do | 4.5.21 | 25.4.21 | We want to save data for future usage
To Do | 12.5.21 | 5.5.21 | Creating TCP protocol | Protocols | Sprint 11 | Concurrency Design Patterns | 9
To Do | 12.5.21 | 5.5.21 | The flight simulator will recive data via TCP
To Do | 12.5.21 | 5.5.21 | Clock and joystick panels will be set to 0 | Flight display | Sprint 12
To Do | 12.5.21 | 5.5.21 | Display list of attributes (CSV)
To Do | 12.5.21 | 5.5.21 | Flight time set to 0 (Flight wont be activated yet)
To Do | 12.5.21 | 5.5.21 | Flight will behavior according to the CVS file
To Do | 12.5.21 | 5.5.21 | Joystick will be represented as a circle inside a circle (wont leave the outer circle boundaries)
To Do | 12.5.21 | 5.5.21 | Joystick will follow CSV file instructions
To Do | 12.5.21 | 5.5.21 | Joystick will move on X and Y axes
To Do | 12.5.21 | 5.5.21 | The user wants the flight to be ready to go after loading all details
To Do | 12.5.21 | 5.5.21 | The user wants to see all flight details (including pilot commands) and plane behavior to detect exceptions
To Do | 12.5.21 | 5.5.21 | Algorithms will be displayed as graphs | Graphs | Sprint 13
To Do | 12.5.21 | 5.5.21 | Create display graph for flight attributes
To Do | 12.5.21 | 5.5.21 | Find and display flight's most correlated attribute on a graph
To Do | 12.5.21 | 5.5.21 | Graphs will be displayed automatically as we press on an attribute
To Do | 12.5.21 | 5.5.21 | Graphs will update automatically as flight continues
To Do | 12.5.21 | 5.5.21 | The user wants to see flight attributes as a graph
To Do | 12.5.21 | 5.5.21 | The user wants to see the differences between different algorithms while fliying
To Do | 12.5.21 | 5.5.21 | The user wants to see the most correlated attribute in a flight as a graph
To Do | 20.5.21 | 13.5.21 | Deadlock protection | Parallel Programming | Sprint 14 | חידושים מגרסה 8 ותרגול דמו של future , completeable Future | 10-11
To Do | 20.5.21 | 13.5.21 | Deadlock protection and multiple users using the app simultaneously
To Do | 20.5.21 | 13.5.21 | Multiple users can change app data simultaneously without running over other user's changes
To Do | 20.5.21 | 13.5.21 | Multiple users can use the app simultaneously without interrupting each other
To Do | 5.6.21 | 21.5.21 | Cache friendly code | Cache friendly code | Sprint 15 | Cache friendly code | 12
To Do | 5.6.21 | 21.5.21 | Improve the code to allow efficient caching
To Do | 5.6.21 | 21.5.21 | Code optimization | Optimization | Sprint 16 | אופטימיזציות קוד, JMV ואופטימיזציות בזמן ריצה | 13
To Do | 5.6.21 | 21.5.21 | Review our code and optimize it as much as we can